## Slide 1: Technical Coordination
Schedule
Final Production
ASIC availability
Number of Wafers
Open issues
Odds and Ends (Action list, weekly report)
1

## Slide 2: Schedule
When to start DEPFET production?
Original plan: September 2011 –
Criticized by referees: test with final electronics before production start
ASIC prototypes available: Nov 2011 (DCD, Switcher, Test_DHP?)
Can this be advanced ? No
Furthermore: SOI availability: needs to be resolved before June 2011
Processing should start latest ~ November 2011
Otherwise increasing risk to miss installation date

## Slide 3: DEPFET processing
PXD6 Processing: Front Side:
16 Months -> 14 Months (delay due to problems with Tracit)
+ only few wafers
- 1 person 3days/week
- complex processing (variations, measurements)
PXD6.2: - >24 wafers (or more ?)
+ 2 persons (5 + 3 days/week)
+ no variants
Count with 14 months as well (for the first sub-batch to be ready)
+ copper (UBM ) (?)
+ back thinning (3 months)

## Slide 4: Schedule
Processing starts: November 2011
Processing ready: End December 2012 (14 Months)
Thinning: Mid April 2013 (3 ½ Months – like PXD6)
Cut, test Mid June 2013 (2 ½ Months)
Start PXD assembly Nov 2013 (finished 1st May 2014)
4 ½ Months to produce 8 good ladders (16 modules)
Module/ladder Assembly
module: flip chip bonding of ASICs, caps 2 weeks (2)
tests 1 week (2)
kapton flex assembly 2 ½ days (2)
ladder joinig & test 1 week (1)
total 4 ½ weeks (1)
one ladder every two weeks:
=> 4 ½ + 7 x 2 weeks = 18 ½ weeks ~ 4 ½ months
after PXD assembly 2 months ‘buffer’ (for ‘tests’)
altogether 4 ½ months of contingency (but better to use it for
tests & commissioning)

## Slide 5: Schedule PXD6.2
2 ½ months between production end and assemble of first module
Use for tests (however: time for copper…)

## Slide 6: Schedule
Slow scenario:
Produce inner ladders, than outers
start inner/outer layer mounting when complete set of ladders is produced (ship together)
Speed up scenario: parallel (alternative), mount as they come: 3 months gained!

## Slide 7: Commissioning
Could gain another ~ 6 months (less time to commission (emergancy)

## Slide 8: Number of Wafers
Need: 16 inner layer modules
24 outer layer modules
Ratio: 2/3
Minimum yield 25%
incl. assembly (?)
24 wafers needed
18 inner
24 outer
Ratio: 3/4
May consider dependence of yield on area
y(outer) = y(inner) 4/3
25% 16% => 32 wafers needed
16 inner
26 outer
Ratio: 2/5

## Slide 9: Open Issues
Radiation hardness
nitride thickness
clear gate
Switcher. Reliability
DHP process: alternatives to IBM 90nm?
DHP/DCE algorithms need MC data
DCD: hope test chip will be a success
SOI: may just be in time…….(my largest worry)
CO2 cooling system(s): who does what where and when?

## Slide 10: Action list
Gets more and more used (people need to be triggered from time to time)
Editor privileges can be granted on request

## Slide 11: Odds and Ends
Weekly report:
please respond! (even if there is no news!)
Twiki:
needs clean up (remove dead wood)
Very useful (especially for newcomers) when up to date

## Slide 12: Thanks!
Thanks to the Bonn group for hosting this workshop!
Next DEPFET workshop:
May 8-11, Ringberg Castle
Don’t miss the superKEKB groundbreaking ceremony!