## Slide 1: Schedule
So far: academic exercise to check if all makes sense
Now: have to convert to a real production schedule with realistic delivery time
Need your input!
Don‘t forget details! (cables & connectors & assembly & testing & labelling)

## Slide 2: Milestones
2013
Extracted from schedule
Given to
Technical coordinator
BPAC
Some delays
mech. And therm mockup
EMCM
PXD6 module
Especially the EMCM has an impact on the overall schedule

## Slide 3: Milestones
Many more milestones extracted from the MS project schedule
Blue:
Official milestones

## Slide 4: Milestones

## Slide 5: PXD9 Production
PXD9 batch one production faster than planned (300d/360, actually 250/360)
Wait for EMCM test befor start of metal layer processing: 8.7.2013
However: EMCM will not be ready till then + time to test!
Hope: production will also be faster
First modules ready July 2014

## Slide 6: PXD9 Production
Chart: 
 | 0 | 7 | 14 | 25 | 25 | 29 | 29 | 30 | 31 | 52 | 60 | 76 | 79 | 81 | 88 | 93 | 95 | 101 | 109 | 112 | 113 | 114 | 119 | 123 | 129 | 133 | 137 | 137 | 141 | 142 | 143 | 148 | 148 | 150 | 151 | 151 | 156 | 160 | 165 | 185 | 189 | 207 | 211 | 212 | 214 | 218 | 221 | 227 | 232 | 233 | 234 | 235 | 237 | 239 | 242 | 246 | 247 | 248 | 262 | 305
 | 0 | 29 | 43 | 50 | 54 | 55 | 57 | 60 | 61 | 62 | 78 | 85 | 87 | 88 | 89 | 90 | 91 | 99 | 102 | 117
 | 0 | 29 | 43 | 50 | 54 | 55 | 57 | 60 | 61 | 62 | 102 | 106 | 109 | 114
Calender
Days
Batch 2: first phase could be finished till December 2013

## Slide 7: Conclusions
Progress:
Test beam: complete readout chain (DCD-DHP-DHH-Onsen)
DESY: RVC works!
Things to worry:
EMCM: already delays the sensor production (though, we learned a lot)
=> speedy testing!
DCD: submission of a new chip, which is of course much better
Do we have time for sufficient testing and a 2nd iteration?
Alternative installation procedure: very tight schedule!
Thermal Mockup: stalled due to work on RVC, MARCO still unreliable