## Slide 1: Status & schedule of ladder parts production
Oct. 2, 2014
Koji Hara (KEK)

## Slide 2: Ladder Parts
Ribs (L3-L6)
Airex sheets
L3 mount bridges
BWD End mounts, APV covers, Kokeshi pins
FWD end mounts (incl. SLM), APV covers, Kokeshi pins
L4-L6 Hybrids
L3 Hybrids
Origame CE, -Z, +Z
Pitch adapters
Pipe clamps (already delivered)
Sensors

## Slide 3
Ribs (L3): already delivered to Melbourne
Ribs (L4, L5, L6):
re-production of CF sheets ongoing
 followed by micro-waterjet-cutting
 Already delivered to assembly sites
Airex sheets (L4, L5, L6):
Already delivered to IPMU

## Slide 4
L3 mount bridges and spacers
  12 sets have been produced for Melbourne
    8 BW, 11 FW are at Melbourne (4 BW, 1 FW are at KEK)
  8 sets (BW are mechanical sample) for DESY thermal mockup
   brought from KEK in this workshop

## Slide 5
BW End mounts, APV covers, Kokeshi-pins
  75 sets are produced
    5 sets are sent to HEPHY for mockup study
  70 sets are at IPMU for L4,5,6
    Ready to use for mockups
    Need to add an additional screw hole for grounding
      New position given by Florian in this workshop
  Additional 40 sets have been produced for DESY thermal mockup
    10 sets brought in this workshop

## Slide 6
FW dummy end mounts without SLM for mockup study
  30 sets of end mounts and Kokeshi-pins produced
  5 sets are sent to HEPHY
  10 L6 APV covers available, but no L4-5 APV cover
FW end mounts with SLM
  120 sets have been produced including those for thermal mockup
    70 sets with L4-5 APV guard
    50 sets with L6 APV guard
  5 sets brought for HEPHY
  5 L4-5 + 5 L6 sets brought for thermal mockup

## Slide 7
L3, L4-L6 FR4 Hybrid boards
  44% of L4/5/6 hybrids completed
  31% of L3 hybrids bonded, 12% tested and shipped

## Slide 8
Pitch adapters 1-layer 3-row
  All 10 types have been produced
    Class B samples also delivered
  10 /type/site good samples
  Issues :
    Short found in “good” samples
    Pad widths of P3B1 pieces of sheet 1 is smaller than others
  Final production will take 1.5 months + contract delay
    Verify the final specification
    Start making contract in Oct.-Nov. in the order of
      1. PF1,2/PB1,2
      2. PA1,2
      3. P3F1,2/P3B1,2

## Slide 9
P3B1-3r.03-XX
Other P3F/P3B

## Slide 10: Short on P3F2-3r.05-01
We have also found other suspicious samples

## Slide 11
The short in P3F/B samples found last week end.
All P3F1,2 /P3B1,2 good samples have been returned to Tokai Denshi
Answer received in Oct. 2 morning
  “it is found short circuit test actually was not performed (!) because of the bad communication between Tokai Denshi and the company performing the test”
    In the previous production >1 year ago, it was.
  Confirming if it is only P3F/B but also in all others
    Also asking possibility to reproduce other 8 types by their responsibility if the test has not been performed

## Slide 12
Pitch adapter 2-layer
  Samples of the initial production has been delivered
    10 / type / site
    B-class samples are also delivered
    Delivery will be finished by June 23
  No plan to produce more

## Slide 13
HPK L3 sensors
  24 good sensors produced, 21 at KEK
    3 have been sent to Torieste and HEPHY for beam test and checks
  11 mechanical samples sent to Melbourne
HPK large
  167 good sensors produced, 160 at KEK
    7 sensors brought to Italy / HEPHY for check
  78 61 mechanical samples
    20 at HEPHY
    1 at Pisa (+ 8 early test production sensors)
    57 40 at IPMU/KEK for L4, L6 and spares for L5 and FW/BW

## Slide 14: Explanation of the excel file
Column H: Assignment. Priority is determined with the radiation level. Better DSSDs should go to inner layers.
Priority | position | Assignments TIFR/HEPHY/IPMU/Pisa | Cumulative sum
1 | L4 barrel | 12+2/0/0/0 | 14
2 | L4 Backward | 0/0/0/12+2 | 28
3 | L5 Barrel | 0/28+4/0/0 | 60
4 | L6 barrel | 0/0/57+6/0 | 123
5 | L5 backward | 0/0/0/14+2 | 139
6 | L6 backward | 0/0/0/19+2 | 160
 | Total | 14/32/63/51 | 160
Proposal
Tsuboyama-san

## Slide 15: Micron Delivery
Micron delivered 83 pcs in total
  56 sensors (until summer)
  3 mechanical samples
  24 sensors on 15th of September 2014
Sensors from all but last shipment have been fully tested (59 pcs.) and qualified
  Stripscan either by Trieste of Vienna
  Longterm stability tests performed on all Micron sensors using Vienna climate chamber
Thomas

## Slide 16: Delivery Status by now
Shipment | Delivered to CERN | Number of sensors | Strip scan done by | Current location
1 | 2 Aug 13 | 2 | Micron & Vienna | Vienna (IPR)
2 | 4 Oct 13 | 4 | Micron & Vienna | Vienna (IPR)
3 | 9 Oct 13 | 7 | Trieste | Vienna
4 | 22 Oct 13 | 4 | Trieste | Vienna
5 | 8.1.2014 | 12 | Vienna | Vienna
6 | 31.3.2014 | 14 | Trieste | Vienna
7 | 30.5.2014 | 13 | Vienna | Vienna
8 | 15.9.2014 | 24 (including replacements for rejects) | to be done | Trieste
Sum: |  | 80 (delivered) | (ordered 60) | 13 rejected so far
Thomas

## Slide 17: Quality
Sensors have been qualified in three Classes:
  Class A: perfectly working: 30 pcs.
  Class B: (working with some minor problems):
  Class C: not working -> mechanical samples
Summary of available sensors:
  Class A: 30 pcs
  Class B: 19 pcs (mostly due to scratches caused by testing in Vienna)
  Class C: 10 pcs (including 3 mechanical samples delivered by Micron)
  Not yet classified: 24 pcs.
Thomas

## Slide 18: L3 parts availability
11 mechanical sensors at Melbourne
Ribs delivered
8 sets of FW/BW bridges + spacers at Melbourne
  More 4 sets are at KEK
3-PF1,PF2,PB1,PB2
  3-row PAs mechanical samples at Melbourne
  “good samples” returned to the company because of short problem
  Final mass production to be completed in 2014 JFY
Hybrid
  Hybrid samples at Melbourne

## Slide 19: FW/BW, L4-6 parts availability
HPK mechanical sensors available at each site
Micron mechanical samples available
Ribs delivered
BW end mounts available
FW end mounts available
Origami
  Mechanical samples available (15 / type / site )
  100% APV equipped, 70% wire-bonded
  Crack problems
PAs
  1-layer 3-row PF/PB/PA delivered
  “good samples” returned to the company because of short problem
  Final mass production to be completed in 2014 JFY
Hybrid delivered
Need to define # of parts for each site

## Slide 20: Status of Produced Origami
Assembled Origami :
wire-bonded/APV glued/Produced at Taiyo total (141 ordered) 102/141/151 +Z (27 ordered) 24/27/31 CE(48 ordered) 33/48/51 -Z (66 ordered) 45/66/69
(assembly is suspended now)
crack scan by CMM microscope
  So far 22 Origamis checked  cracks found in all of them
  Photographs of 512 pads are taken for each Origami PA0
   damaged pads counted by eye-scan of them for 19 Origamis
Electrical probe test of assembled Origami PA0, PA0 to be produced for repair
    Discussing Taiyo
    The company used by Tokai Denshi answers us they can do the test of PA0.

## Slide 21: PA0 history and crack
Cracks have been overlooked in Taiyo’s check (visual inspection)
We have checked Origami samples we have
Pre-production before 2013 Oct.
  No cracks found
Modification of glue between PA0 layers in 2013 oct.
  Acrylic glue -> epoxy glue
    For radiation tolerance and to reduce curvature around PA0
    Accompanying cover sheet under the glue was also changed
  Cracks observed
Final production in late 2013
  Found cracks in all samples we have checked so far

## Slide 22
Fraction of pads with crack
(crack on the pad itself excluded)
Pad position

## Slide 23: Improved PA0 production
Taiyo is trying to improve the production process
  New blanking mold
  Different glue between PA0 and Origami
    Accompanied with different cover sheet on the glue
    Glue between PA0 top and bottom layer is kept same
Taiyo made repaired Origami sample with new PA0 glued on existing PA0
 Quality checked on Sep. 29 at KEK

## Slide 24
Still find many cracks on both layers
Also in the APV-side

## Slide 25
Before
After
The cracks after the modification are small but still there
Sample returned to taiyo
Taiyo is checking
Need more iteration

## Slide 26: Solution for PA0 problem
Need to produce crack-free PA0
  Must be electrically tested
Two possible (not impossible) ways
  a) Gluing new PA0 without cracks on existing Orgami PA0
  b) Full reproduction of Origami

## Slide 27: Crack-free PA0 production
First trial at Taiyo was not successful
  Smaller but many cracks
  Taiyo is investigating the sample
Need more iteration
  1st trial done in a month
   another trials  expect to 3 months for 3 trials
  2 weeks for the final production
Electrical test
  The company used by the tokai denshi can do the test of PA0
  Cost is about 550 Yen/piece  ~90,000 JPY @150 pieces
  < 2 weeks (machine program and test of 150 pieces)

## Slide 28: Gluing option
Gluing on existing PA0
  Precise positioning is doable with existing alignment holes
  Gluing without bubble is the key issue
    Step between top and bottom layer
  Selection of glue
Two options
  Gluing by Taiyo
    Acrylic-type glue sheet, hot pressed by small bars, avoiding touching APV and wires
    1 month
  Gluing by REPIC
    Using araldite, cured in room temperature for one day
    REPIC has experience of the similar situation
    2 months
  Gluing by REPIC is better

## Slide 29: Taiyo glued sample
Bubbles between pads but not under the pads

## Slide 30: Full reproduction
Need to procure parts  basically available
  APV chips  available at CERN (diced), thinning possible (need to test to get the yield)
  Connectors  500 connectors already bought by HEPHY
Origami + PA0 full production at Taiyo
Reflow soldering, APV gluing, APV wire bonding (control lines) at REPIC

## Slide 31: Rough Cost and Delay Estimation
Crack-free PA0 production 4 months
Gluing option : 2 months
  Expect Taiyo + REPIC to pay by themselves
    Taiyo already showed their will do so, for gluing option at Taiyo
    Additional electrical test ~ 90,000 yen  payable
Full reproduction option : 6 months
  Origami + PA0 production + assembling parts + bonding
  Origami assembly : 25 M JPY
    Some of them must be paied by Taiyo + REPIC
  APV cost (2500 chips) : 5 M JPY (chip 4.3M, thinning 0.7M)

## Slide 34: The quality of DSSD is evaluated
(i) Bias current at 200 V ( for the long-term stability and radiation tolerance)
(ii) Number of AC-coupling and aluminum-trace failures (Preventing the punch-through current flowing into APV25, especially after installation)
(iii) Number of implant errors on the p side (DC measurement) The formula is shown below

## Slide 35: The quality of DSSD is evaluated
e) Then I assigned which DSSD goes to each site.
  Better DSSDs are assigned in the inner layers because of the higher radiation level.
f) In order to distribute enough numbers of DSSDs to each site, I included the DSSDs diced with saw, not with laser.
g) DSSDs with serial number less than 64 and 80-86 are treated as R&D DSSD.

## Slide 36: Explanation of the excel file
Column A-E: Bar code , batch, delivery date.
Column F: The present site where the DSSD is stocked.
Column G: Quality index
  Q=(10-Ib(200V))*(60-P_badstrips)*(10-P_couplingerror)(10-Ncouplingerror)
  Q>0: The quality is acceptable.
  Q==0: The quality is quite poor or the DSSD has been used or lost already.
  0>Q>-100 (Calculation: Q=Q-100 for ID<64.)
    These DSSDs have been distributed already for tests and R&D.
    The DSSDs with 0>Q>-50 are good sensors. though they were produced in the early stage.
  Q=-100: quite poor quality or unusable DSSD with ID<64