## Slide 1: PXD
DEPFET Sensor Production
Belle II Schedule
AIM Decision
EPICS
H-.G. Moser, 18th B2GM, June 2014

## Slide 2: PXD9 Production
Chart: 
pxd 9-2 | 0 | 7 | 14 | 25 | 25 | 29 | 29 | 30 | 31 | 52 | 60 | 76 | 79 | 81 | 88 | 93 | 95 | 101 | 109 | 112 | 113 | 114 | 119 | 123 | 129 | 133 | 137 | 137 | 141 | 142 | 143 | 148 | 148 | 150 | 151 | 151 | 156 | 160 | 165 | 185 | 189 | 207 | 211 | 212 | 214 | 218 | 221 | 227 | 232 | 233 | 234 | 235 | 237 | 239 | 242 | 246 | 247 | 248 | 262 | 305
pxd 9-3 | 0 | 29 | 43 | 50 | 54 | 55 | 57 | 60 | 61 | 62 | 78 | 85 | 87 | 88 | 89 | 90 | 91 | 99 | 102 | 117 | 118 | 119 | 123 | 125 | 127 | 134 | 136 | 138 | 139 | 144 | 147 | 151 | 152 | 153 | 154 | 154 | 155 | 158 | 166 | 168 | 169 | 187 | 189 | 190 | 193 | 195 | 197 | 210
pxd 9-4 | 0 | 29 | 43 | 50 | 54 | 55 | 57 | 60 | 61 | 62 | 102 | 106 | 109 | 114 | 119 | 121 | 127 | 134 | 138 | 147 | 151 | 153 | 155 | 169 | 187 | 190 | 193 | 194 | 195 | 196 | 197 | 211 | 213 | 215 | 216 | 218 | 221 | 227 | 229 | 232 | 235 | 242 | 244 | 246 | 252 | 256 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 272 | 273 | 274 | 275 | 288
pxd 9-5 | 0 | 7 | 24 | 26 | 27 | 28 | 34 | 40 | 41 | 42 | 63 | 66 | 68 | 70 | 94 | 96 | 98 | 101 | 103 | 119 | 124 | 125 | 126 | 140 | 144 | 147 | 150 | 154 | 164 | 165 | 166 | 171 | 172 | 173 | 174 | 175 | 175 | 182 | 193 | 194 | 195 | 196 | 201 | 203 | 206 | 208 | 210 | 213 | 214 | 215 | 216 | 217 | 221 | 223 | 224 | 226 | 227 | 228 | 231 | 236
Batch 1 phase 1 finished:
Batch 2 lost after 80% of phase 1
Batch 3 phase 1 finished
Batch 4 phase 1 finished (June 2014)
Calender Days
Production steps
Batch 1
Batch 3
Batch 2
Batch 4

## Slide 3: Yield after phase 1
So far this is encouraging
Still, more production steps with possible losses ahead
Need perfect QA,
eliminate possible losses,
use grade 2 & 3 for prototyping and tests (irradiations, beast)
Search for possible defects (optical scan, automatic & manual)

## Slide 4: Test of metal system processing with EMCM
Test vehicle to optimize yield of metal system without the time consuming
(and expensive) phase 1
=> EMCM: Electrical Dummy to be tested like a real module
Allows tests of the electrical performance
- routing errors (despite automatic checking tools)
- cross talk, voltage drops, RC delays
EMCM3: several (optimized)
process variations
Wafers 17 and 18 show best results,
Essentially 100% yield
Confirmation batch (EMCM4) processed
Tests started, so far confirm good results of EMCM3

## Slide 5: Schedule: Plan A2 (default)
+ 8 months
+ 8 months
=> Already obsolete (T. Browder)

## Slide 6: Plan A3
+ 9 months
+ 9 months
Belle II proposal

## Slide 7: Plan A4
+ 12 months
+ 10 months

## Slide 8: Plan C4
+ 12 months
+ 12 months

## Slide 9: Schedule: Summary
Plan | Beast II PXD @ KEK | DT months | Installation VXD | DT months
original | Feb. 2016 |  | July 2016 | 
A2 | Oct. 2016 | +8 | Mar. 2017 | +8
A3 | Nov 2016 | +9 | Apr. 2017 | +9
A4 | Dec 2016 | +10 | July 2017 | +12
C4 | Feb 2017 | +12 | July 2017 | +12
Assuming: PXD/SVD integration parallel to Beast II run
Minimum delay: 8 (9?) months
Though unlikely A2 is still default till EB decision
TOP may be complete in A2 - but do not plan on this (TC)

## Slide 10: PXD Schedule
After BPAC: shifted PXD delivery to KEK from September 15 to February 16 (synchronize with SVX integration, already outdated).
Phase 2 processing delayed to October 2014 (wait for EMCM electronic test).
Still compatible with present, outdated schedule (contingency: 8 months)

## Slide 11: Milestones
PXD9 Production start | July.12 | 
cable prototypes | November 12 | 
EMCM fabricated | Mai 13 | 
Services available | December 13 | 
Mechanical & Cooling Mockup ready | April14 | August 14
PXD6 large matrix assembled | December 13 | 
PXD/SVD sector test | January14 | 
DAC and DHH available | March14 | August 14
Power supplies available | March 14 | 
Metal layer processing starts | April 14 | October 14
All production ASICs available | September 14 | March 15
assembly tooling finished | October 14 | 
First Belle II DEPFET sensors available (cut & tested) | November 14 | April 15
IBBelle (CO2 cooling) constructed | December 14 | 
ladder 0 (prototype) assembled | December 14 | June 15
all sensors available | August 15 | January 16
all ladders assembled | August 15 | January 16
PXD ready for integration | September 15 | February 16
Some delays due to late
start-up of phase 2 sensor processing

## Slide 12: AIM
Satellite Meeting June 17 & 18
Demonstration of RVC (ok after ½ year under vacuum at KEK)
Demonstrations using mock-ups of standard and alternative installation (AIM)
-> New: demonstration of emergency de-installation (EDI)
Decision:
AIM becomes baseline
Our homework: increase clearance for cables around RVC/QCS
=> replacement of ½ of Infiniband data cables by thinner CAT5 cables

## Slide 13: EPICS
EPICs will be used in Belle II (SVD, PXD, …..), in addition to NSM2
CSS will be used as common access to EPICs and NSM2 (top layer)
NSM2/EPICS gateway for direct communication

## Slide 14: Summary
PXD: phase I of sensor production competed
good yield of phase I
inter-metal insulation problems solved -> start phase II in October
Schedule: delay by at least 8/9 months due to funding shortage
AIM: accepted as baseline
EPICS: will be used in Belle II
Other Topics:
Background: cannot be resolved by reducing magnetic field
(1.5 T still baseline, 1.2 T as ‘backup’)
Grounding scheme and rules
New monthly meeting on integration work and logistics