## Slide 1: BPAC Report
7th Belle II VXD Workshop, Prague

## Slide 2: Introduction
SVD production readiness review
  9th -10th Nov. 2014 at Kavli IPMU
  Focused on production readiness
  But also cooling, electronics, etc.
Final report received few days ago
  http://kds.kek.jp/materialDisplay.py?materialId=0&confId=16766
  More than 5 pages of concerns and recommendations
  Almost the whole report is a list of recommendations
  Have to consider them seriously!

## Slide 3: Concerns (1) - Delay
6 months to get new FlexPA design
Still not in production!
Origami PA0 problem
What else have we overseen?
Fully functional ladder: Need to build it as soon we have new working and tested Origami hybrids!

## Slide 4: Concerns (2) – Thermal Mockup
Thermal mockup not ready before end of 2015
Ladder production has to start earlier
Should perform additional thermal tests and studies with simpler setups
  Thermal cycling of single class C ladders

## Slide 5: Concerns (3) – Noise & Grounding
CF ground connection might be possible solution for outer shell (and cones)
Not applicable for ribs  cut from pre-preg plates
Need to do intensive noise tests

## Slide 6: Recommendations

## Slide 7: General Recommendations (1)
Build fully working ladder as soon as possible
Need to complete inventory of HPK sensors first
Can build L5 ladder with pre-production Origami hybrids soon
What about other layers?
Do we have enough sensors, in particular for L3?

## Slide 8: General Recommendations (2)
Additional thermal tests and verifications
Consider to give up contingency at the end of production
  Should use time needed to re-produce Origami hybrids as good as possible for thermal tests on class C ladders

## Slide 9: Organization & Schedule
Re-organization of group appreciated, but should go even further  topic @ SVD IB tomorrow
Define set of high-level and lower-level milestones
Closely monitor progress

## Slide 10: Reasons of PA issues
Need to review specs of remaining items  on the way
Monitor companies closely
No changes or modification during production
  If unavoidable: notify group, verify changes, sing-off of revised specs
Avoid to repeat these problems

## Slide 11: Ladder Construction
Requirements are not well defined
Have to discuss within the QCG how we can prepare quantitative requirements
Moreover we need specifications for all components, ladders, etc.

## Slide 12: Number of Spares
Only 20% spares  probably not enough
Need to complete inventory to be able to calculate the possible number of spare components we can build.
E.g. there are still HPK sensors in the database with unknown location.

## Slide 13: Forward / Backward Modules
Good news: Module production in good shape
Pisa group shall take over an active role, also in preparation for ladder production
  Recent commitment: Filippo will contribute to design ladder mount procedure  method to attach ladders from top

## Slide 14: Layer 4
Main concerns: Schedule to build class C, manpower and travel plan of TIFR personal  more overlap, avoid long absence from assembly

## Slide 15: Layer 5
HEPHY people are aware of this
Discussion HEPHY internal and with SVD IB ongoing
Strongly related to SVD group organization  SVD IB

## Slide 16: Alignment and SVD Support
Focus on one method to assemble SVD structure and mount ladders  people actually doing the work should decide
Measurement during ladder mount well considered, but how do we calibrate the tool?

## Slide 17: Electronics and Grounding (1)
Adequate ground connection of all electrical conductors
Carbon fiber should be considered as conductor
Testing at early stage to understand noise levels

## Slide 18: Electronics and Grounding (2)
Committee is concerned about noise
Strong recommendation to build electrically working ladder as soon as possible and perform intensive tests on it.
Even though the ladder has some known issues (e.g. dead chips)

## Slide 19: Thermal Management (1)
Results from thermal mockup-up might come too late
Carry out FEA studies and test for critical issues
Perform thermal mockup tests as early as possible

## Slide 20: Thermal Management (2)
How to achieve homogeneous airflow in (warm/cold) dry volume?
VXD group is encouraged to prepare inventory of interlock and powering behavior
Define complete set of failure scenarios

## Slide 21: Summary
Final report of SVD review released recently
Long list of concerns and recommendations
Main recommendations:
  Improve SVD group leadership
  Separate construction tasks from management
  Build electrically working ladder as soon as possible
  Detailed investigation of noise behavior
  Thermal mockup will be late  perform FEA and additional thermal tests on critical items asap

## Slide 22: Thank You!