## Slide 1
Pilot Run - Status and Plans
PXD9-6
Rainer Richter
for the MPG Halbleiterlabor

## Slide 2: Pilot run wafers
Batch | W | Type | Contacts | Testing status
I | 24 | dummy | to poly, poxn, noxn | ongoing
I | 25 | dummy | to poly, poxn, noxn | ongoing
I | 26 | dummy | to poly, poxn, noxn | ongoing
I | 27 | dummy | to poly, poxn, noxn | ongoing
II | 23 | dummy | all | from 26.01.15
II | 30 | hot | all | from 26.01.15
II | 35 | hot | all | from 26.01.15
II | 36 | hot | all | from 26.01.15

## Slide 3: PXD9-6 production status
- first metal (al1n)
Al deposition, lithography, etching done
first electrical measurements (talks by Paola and me)
- metal1 metal2 vias (co2n)
lithography and etching done
- second metal (al2n)
Al deposition (all wafers) done
lithography and etching (dummies) done
lithography and etching (project wafers) done
(still in inspection)
Break for intense measurements
can start next week

## Slide 4: Module label
Containing:
Wafer number and module type
-> unique labels
150µm height
-> magnifying glass

## Slide 5: Summary
PXD9-6 production (pilot run) is running smoothly and in time
1 week ahead of schedule
first electrical measurements (after metal 1) look promising
(see next talks)
Now: metal 2 is finished
Top side of the DEPFET matrix is ‚ready‘ (does not need copper)
Intense measurements are planned in the next 2-3 weeks

## Slide 6: PXD9 Pilot production (iii)
Cons
- Risk to loose of 2 or 3 (2nd grade) PXD9 wafers
if we finally find still a severe bug on EMCM modules
- No time to wait with the remaining wafer on the results of fully equipped and tested modules
But we could wait with the first batch for the intermediate
tests of metal1/metal2
And we could stop before Copper in order to be able to react in the third metal layer on unforeseen results (e.g. Gated Mode)