## Slide 1: VXD Monitoring and Interlock Sub-group organization, tasks and schedule
L.Vitale
INFN and Univ. Trieste

## Slide 2: Outline
SVD organization
Sub-group organization
  Initials Tasks and modifications
  Work packages
  Financial plan
  Schedule
  Documentation

## Slide 3: SVD organization

## Slide 4: Initial tasks and modifications
SVD Radiation monitoring
  Fast ~10um monitoring to protect SVD (beam abort)
  Keep track of the Long Term accumulated dose
SVD Environmental monitoring
  Temperature
  Humidity
Evolved including
  PXD radiation monitoring (VXD general task as Humidity)
  BEAST2 participation both phase1&2,
  FOS to monitor more points
  interlocks

## Slide 5: Work packages and people involved
VXD radiation monitoring and Beam Abort (L.Vitale)
  Sensors (LV, LB, LL)
  RO Electronics (Elettra + LL LV)
  Simulations (Gianluca Inguglia?)
  Software EPICS (Simon Bacher?)
SVD Temperature with NTC (L.Lanceri?)
  Hardware and lab software (PC, LL)
  Software EPICS (Simon Bacher?)
SVD Temperature with FOS (L.Vitale)
  Hardware, lab software + calibration (LV, LL, TS techn, + help from PXD)
  Software EPICS (Simon Bacher?)
VXD Humidity (L.Lanceri?)
  Hardware and lab software (LL, LV)
  Pipes (MPI, DESY, KEK)
  Software EPICS (Simon Bacher?)
Interlock with PLC (L.Lanceri?)
BEAST2 (L.Vitale)

## Slide 6: Interactions
SVD Monitoring Sub-group
VXD radiation monitoring and Beam Abort
SVD Temperature with NTC
SVD Temperature with FOS
VXD Humidity
Interlock with PLC
BEAST2
SuperKEKB, Other BELLE2, SVDSub-groups
SuperKEKB
BEAST2
Outer Detector mechanics
VXD mechanics
SVD mechanics
SVD commissioning
SVD software (slow control, simulation, ect.)
SVD electronics (Power supplies, …)

## Slide 7: Interactions

## Slide 8: Financial plan and WBS
We have already prepared a WBS (Work Breakdown Structure) in excel
  to plan, foresee and keep track all activities and money flows (INFN Trieste side)
  Need few updates
Other financial supports for specific activities
  For BEAST2 (Carlos, Katsuro)

## Slide 9: Approximate schedule (as ~Oct.2014)
Temperature & humidity | 2014 |  |  |  | 2015 |  |  |  | 2016 | 
What | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
T&H Specifications, sign up |  |  |  |  |  |  |  |  |  | 
Fibers, mechanical layout |  |  |  |  |  |  |  |  |  | 
Fibers, assembly tests (SVD) |  |  |  |  |  |  |  |  |  | 
Fibers, multiplexing scheme |  |  |  |  |  |  |  |  |  | 
Fibers design sign up |  |  |  |  |  |  |  |  |  | 
Procurement, assembly |  |  |  |  |  |  |  |  |  | 
installation (PXD & SVD) |  |  |  |  |  |  |  |  |  | 
Thermistors, lab tests |  |  |  |  |  |  |  |  |  | 
Mechanics & cabling design |  |  |  |  |  |  |  |  |  | 
Procurement |  |  |  |  |  |  |  |  |  | 
assembly, installation |  |  |  |  |  |  |  |  |  | 
Radiation | 2014 |  |  |  | 2015 |  |  |  | 2016 | 
What | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Specifications, sign up |  |  |  |  |  |  |  |  |  | 
Simulations |  |  |  |  |  |  |  |  |  | 
Dosimetry, characterization |  |  |  |  |  |  |  |  |  | 
Diamond sensors choice |  |  |  |  |  |  |  |  |  | 
Mechanics & cabling design |  |  |  |  |  |  |  |  |  | 
Electronics specifications |  |  |  |  |  |  |  |  |  | 
Electronics design & proto. |  |  |  |  |  |  |  |  |  | 
Overall design, sign up |  |  |  |  |  |  |  |  |  | 
Components, procurement |  |  |  |  |  |  |  |  |  | 
"final" prototypes (4 ch.) |  |  |  |  |  |  |  |  |  | 
BEAST, 1 preliminary tests |  |  |  |  |  |  |  |  |  | 
BEAST, 2 complete test (4 ch) |  |  |  |  |  |  |  |  |  | 
electronics production & test |  |  |  |  |  |  |  |  |  | 
sensors installation & cabling |  |  |  |  |  |  |  |  |  | 
electronics installation |  |  |  |  |  |  |  |  |  | 

## Slide 10: Approximate schedule (Jan.2015) TBU
Temperature & humidity | 2014 |  |  |  | 2015 |  |  |  | 2016 | 
What | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
T&H Specifications, sign up |  |  |  |  |  |  |  |  |  | 
Fibers, mechanical layout |  |  |  |  |  |  |  |  |  | 
Fibers, assembly tests (SVD) |  |  |  |  |  |  |  |  |  | 
Fibers, multiplexing scheme |  |  |  |  |  |  |  |  |  | 
Fibers design sign up |  |  |  |  |  |  |  |  |  | 
Procurement, assembly |  |  |  |  |  |  |  |  |  | 
installation (PXD & SVD) |  |  |  |  |  |  |  |  |  | 
Thermistors, lab tests |  |  |  |  |  |  |  |  |  | 
Mechanics & cabling design |  |  |  |  |  |  |  |  |  | 
Procurement |  |  |  |  |  |  |  |  |  | 
assembly, installation |  |  |  |  |  |  |  |  |  | 
Radiation | 2014 |  |  |  | 2015 |  |  |  | 2016 | 
What | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Specifications, sign up |  |  |  |  |  |  |  |  |  | 
Simulations |  |  |  |  |  |  |  |  |  | 
Dosimetry, characterization |  |  |  |  |  |  |  |  |  | 
Diamond sensors choice |  |  |  |  |  |  |  |  |  | 
Mechanics & cabling design |  |  |  |  |  |  |  |  |  | 
Electronics specifications |  |  |  |  |  |  |  |  |  | 
Electronics design & proto. |  |  |  |  |  |  |  |  |  | 
Overall design, sign up |  |  |  |  |  |  |  |  |  | 
Components, procurement |  |  |  |  |  |  |  |  |  | 
"final" prototypes (4 ch.) |  |  |  |  |  |  |  |  |  | 
BEAST, 1 preliminary tests (mod.) |  |  |  |  |  |  |  |  |  | 
BEAST, 2 complete test (4 ch) |  |  |  |  |  |  |  |  |  | 
electronics production & test |  |  |  |  |  |  |  |  |  | 
sensors installation & cabling |  |  |  |  |  |  |  |  |  | 
electronics installation |  |  |  |  |  |  |  |  |  | 
= internal
milestone
= shifted
= just ✓ or in progress
= needs SVD
Sign off

## Slide 11: Documentation
Wiki page: existing, TBU
Internal documentation:
  General requirements: ✓
  Mechanics and Cabling: TBD
  Progress on diamonds sensors: TBD
  Radiation Electronics: TBD (some material)
  SVD NTC: ~✓
  SVD FOS: TBD (only initial project)
  VXD Humidity: TBD (only initial project)
  VXD interlock: TBD (only initial project)
  WBS: ✓TBU

## Slide 12: Meetings
Specific Parallel SVD sessions at VXD workshops and B2GM
Reports at B2GM Background session
Specific meetings when needed (need at least monthly updates on progress, issues, etc.)
Periodic reports at SVD weekly meeting

## Slide 13: Back-up slides