## Slide 1: Belle II Schedule
Yutaka USHIRODA
Jan. 2015

## Slide 2
SuperKEKB/Belle II Schedule
Nov. 9, 2014
JFY2018
2018
2014
JFY2014
2015
2016
2017
JFY2015
JFY2016
JFY2017
Japan FY
now
Calendar
Power restriction
in summer
phase 1
phase 2
phase 3
Start-up
QCS, Belle II install
VXD install
(B) JFY2015 budget ◯◯ Oku-Yen
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
w/ full Belle II
phase 1
phase 2
phase 3
Start-up
QCS, Belle II install
VXD install
Current plan ongoing
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
w/ full Belle II
phase 1
phase 2
phase 3
SuperKEKB Construction
Start-up
QCS, Belle II
VXD install
Original plan
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
w/ full Belle II
phase 1
phase 2
Start-up
QCS, Belle II install
VXD install
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
JFY2014 Operation budget cut by 12 Oku-Yen
Detailed estimation of inter-phase schedule: 11 months for phase 1->2, 6 for phase 2->3.
(A) JFY2015 budget △△ Oku-Yen
SuperKEKB Construction
SuperKEKB Construction
SuperKEKB Construction
Power restriction
in summer
Power restriction
in summer
phase 3
w/ full Belle II
Power restriction
in summer
Desirable budget
Conceivable budget
Prospect will be clearer in the very end of Dec.
Tragic

## Slide 3: Timeline
* delayed due to Lower House election
Jan. 9, 2015 Cabinet Decision of JFY2014 supplemental budget
Apr. 10, 2015
Congressional Approval
Jan. 14, 2015*
Cabinet Decision of JFY2015 budget
MOF
MEXT
KEK
IPNS, Acc. Lab
Belle II, SuperKEKB
19a
９６兆３４２０億円
３兆１１８０億円
20p
[private, preliminary announcement from Yamauchi-san]
Dear Tom, The JFY2015 budget was informed by MEXT today. KEK's international projects were given maximum considerations by MEXT, which will allow us to start the phase-1 commissioning early next year. We thank you once more for your great help. Please share this information with the Belle II colleagues. Best regards, Masa Yamauchi

## Slide 4: Possible new schedule (tbc)
Difficult to interpret what Yamauchi-san’s brief notice means, but assume phase 1 starts as “early” as Jan. 2016 (=conceivable budget scenario)
Start of TOP installation += 2mo.

## Slide 5: TOP Assembly “dry runs” + 1st module
Dry runs towards 1st Belle II TOP counter assembly
  Practice using actual assembly systems and jigs on mechanical dummy (glass)
The first real TOP module completed
All 16+2 modules to be made in 1 year

## Slide 6: Module 01 after a month
Found quartz glue joint has failed
module production suspended
~8 weeks of delay for additional studies

## Slide 7
Hot news!
CDC moved from Fuji to Tsukuba
Jan. 21st, 2015

## Slide 9
SuperKEKB/Belle II Schedule
Jan. 13, 2015
JFY2018
2018
2014
JFY2014
2015
2016
2017
JFY2015
JFY2016
JFY2017
Japan FY
now
Calendar
Power restriction
in summer
phase 1
phase 2
phase 3
Start-up
QCS, Belle II install
VXD install
(B) JFY2015 budget ◯◯ Oku-Yen
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
w/ full Belle II
phase 1
phase 2
phase 3
Start-up
QCS, Belle II install
VXD install
Current plan ongoing
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
w/ full Belle II
phase 1
phase 2
phase 3
SuperKEKB Construction
Start-up
QCS, Belle II
VXD install
Original plan
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
w/ full Belle II
phase 1
phase 2
Start-up
QCS, Belle II install
VXD install
w/o QCS
w/o Belle II
w/ QCS
w/ Belle II (no VXD)
JFY2014 Operation budget cut by 12 Oku-Yen
Detailed estimation of inter-phase schedule: 11 months for phase 1->2, 6 for phase 2->3.
(A) JFY2015 budget △△ Oku-Yen
SuperKEKB Construction
SuperKEKB Construction
SuperKEKB Construction
Power restriction
in summer
Power restriction
in summer
phase 3
w/ full Belle II
Power restriction
in summer
Desirable budget
Conceivable budget
Prospect will be clearer in the very end of Dec.
Tragic
* delayed due to Lower House election

## Slide 10: Detector Construction Schedule
A) Conceivable

## Slide 11: Detector Construction Schedule
B) Desirable

## Slide 12
3 months difference in start of phase 1
6 months difference in start of VXD installation
9 months difference in start of phase 3
Phase 2 planning is more important in conceivable scenario as split into two