## Slide 1: Origami, PA
2015 Sep. 10
Koji Hara (KEK)

## Slide 2: Origami Status
PA0 Production
APV
Origami Assembly Specification

## Slide 3: PA0
171 (159 + 22) PA0 produced and electrically tested
    104 OK
    67 NG (shorts)
  Now At KEK  sent back to Taiyo on Sep. 10
    checked for cracks (5 + 1 pieces) at KEK  No cracks
3rd batch 76 pieces produced. Now at Taiyo
  Scheduling electrical test.

## Slide 4: APV
Cleaning and inspection after cleaning completed on Sep. 10
Good APVs w/o cleaning : 1219
Cleaning result
433 dirty chips  387 “good” (338 + 49 (manual cleaning) )
visual inspection again  384 good (3 cracks)
Already used for batch0: -120
Received 100 Good chips from HEPHY today
Good APV chips in hand : 1219+384-120 + 100 = 1583 (1410 at least needed)
+173 (+12%) spare chips  seems to be enough

## Slide 5: Origami Spec.
Discussed with REPIC (and Taiyo)
  No problem in the technical things
    Some minor things
  Needed to clarify the responsibility if failure happens
Visual inspection of bonding pads after reflow
  Inspection of both APV-side and Sensor-side will be done
Minor things

## Slide 6
Electrical Tests
  Step 1
All bare Origami flexes must be electrically tested
…
All bare PA0’s are also electrically tested … After this PA0 test, further processing shall only happen after the test results are analyzed by the client and he approves of going ahead. …
  Step 2
Once the Origami flex is assembled with components and reflow is done, PA0 must be electrically tested again against opens and shorts, because the reflow process may cause some damage. After that test, further processing shall only happen after the test results are analyzed by the client and he approves of going ahead. …
Step 3
After assembly of all parts, including the chips and wire-bonding, the fully populated Origami undergoes an electrical test at KEK. …
All Origami flexes which pass this test (and all other test before including visual inspection) are deemed as accepted
…
Here are two things:
The Origamis failed these test cannot be used for assembly of Belle II SVD.  Obvious
Who takes responsibility of reproducing Origami, PA0 and parts if bad Origamis found in these step ?  Need to be clarified and agreed with the company (REPIC)
  REPIC cannot be responsible for the quality of APV chips found to be bad in step 3.

## Slide 7: Responsibility of Origami reproduction If bad Origami+PA0 is found
REPIC (actually Taiyo) takes responsibility of
  Producing 141 Origami passing electrical test
  Producing 141 PA0 passing electrical test
After SMD parts assembly by reflow soldering
  REPIC will reproduce Origami and PA0 only
  If there is clear fault in the process.
  If wire bonding found to be is impossible due to solder drop on the pad.
After APV gluing + wire bonding
REPIC will reproduce Origami and PA0 only
  If there is clear fault in the process.
Otherwise KEK will be responsible to reproduce Origami and PA0
In any case, connectors and APVs should be provided by KEK

## Slide 8: Spare Origami and PA0 at Taiyo
Origami At Taiyo
  10 Origami –Z
  6 Origami +Z
  19 Origami CE
  Those are available for spare without additional cost.
PA0
  Additional good pieces passing electrical test will be available for spare.
  So far 104 good (67 bad), 76 to be measured
    I hope good yield

## Slide 9: Bonding position for Bias check
No specific request on spec.
Any preference?
For batch0 no request sent  bonded at the center b)
REPIC says c) is OK but a) is not
if need to be at the end of pad
a)
b)
c)

## Slide 10: Origami Spec. Minor things
Serial Numbers and Tracking
13.1. PA0
In order to track the history and measurements of each PA0, a unique serial number shall be assigned to every PA0 in the format “PA0.nnn” (regardless of wide or narrow pad type), and nnn is a 3-digit number, starting from 000.
This serial number shall be attached to the envelope of the PA0 by the manufacturer (probably using a barcode for convenience) and may also be written onto an inactive region of PA0 with felt pen (maybe in short form “nnn”, omitting the obvious “PA0” prefix).
Electrical measurement data of PA0 shall always refer to the respective PA0 serial number – or to the Origami flex serial number, after the PA0 is attached to it.
When PA0 is glued onto an Origami flex, the matching serial numbers of both objects shall be recorded in an Excel table and provided to the client.
Already started from 001
No such barcode prepared
Other things are OK

## Slide 11: PA 2nd production + replacement of bad PAs
Pad width measurement is on-going
  280 (2nd prod.) + 61 (replacement of 1st bad PAs)
  280 measured ( good 269, bad(<30um) 11 )
  61 still to be measured (30 PB2, 30 PF2, 1 PA1)
    Will be measured on 9/19 (and 26) (Sat.)
Replacement of bad (<30um) PA
  61 pcs for 1st delivery already delivered and measured
  11 pcs for (2nd delivery + 1st replacement measured so far) to be delivered on Sep. 14

## Slide 12: PA Production and width measurement status
 | Ordered | Width OK | Sent for visual inspection | Remaining pieces
P3F1 | 30 | 30 | 19@Melbourne | 
P3F2 | 30 | 30 | 14@Melbourne | 
P3B1 | 30 | 30 | 20@Melbourne | 
P3B2 | 30 | 30 | 17@Melbourne | 
PF1 | 100 | 100 | 29+39@Pisa | 
PF2 | 100 | 70 | 20+38@Pisa | 30 pcs not measured
PB1 | 100 | 98 | 26+36@Pisa | 2 pcs delivery on Sep. 14
PB2 | 100 | 70 | 23+@Pisa | 30 pcs not measured
PA1 | 200 | 192 | 57@HEPHY | 1 pc not measured. 7 pcs delivery on Sep. 14
PA2 | 200 | 198 | 60@HEPHY | 2 pcs delivery on Sep. 14