## Sheet1
| 2015 | [23 empty] | 2016
| May |  |  | June |  | July |  | August |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  | January
Concrete shield(gate) | [18 empty] | Install | [6 empty] | Ono/Kanazawa
Wall shield | [22 empty] | Install |  |  | Ono
[19 empty] | ● | ● | ● | ● | ● | ●
Concrete shield block | [12 empty] | *Scaffold(14Sep-), Install(24Sep-15Oct)* | [12 empty] | Kanazawa
[13 empty] | ● | ● | ● | ●
Beam pipe | Install/connection | [24 empty] | Suetsugu/Kanazawa
IP1 |  |  |  |  | Install(22Jun-3Jly) | [20 empty] | Kanazawa
Removal of cooler unit |  | (18-19May) | [23 empty] | Terui
Removal of deck |  |  | (25-29May) | [22 empty] | Kanazawa
|  | ● | ● |  | ●
Magnet | Install | [24 empty] | Masuzawa
Survey |  |  |  | Survey
Alignment | [7 empty] | Alignment
Powering test | [25 empty] | Tokuda
●
QCSR He line | [25 empty] | Kawai
[11 empty] | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
QCS cable | [10 empty] | * | [14 empty] | Oki
Boring of Acc. floor | [9 empty] | * | [15 empty] | Yamaoka
Removal of magnet switch boad | [6 empty] | 23-24Jul | [18 empty] | Kanazawa
Detachment of Y-fence from safety system | [9 empty] | 24Aug | [15 empty] | Mimashi
LABM optical line | [14 empty] | ●(1Oct) | [5 empty] | ●15Nov |  |  |  |  | Flanagan
Dithering coil setting |  |  |  | 1-5Jun | [21 empty] | Masuzawa
Beast 1 |  |  |  |  | Cable(27Jun-3Jly) |  |  |  | *Support and Sensor(17Aug-18Sep)* | [16 empty] | Nakayama
Luminosity monitor | [25 empty] | Uehara
Belle II | [25 empty] | Adachi
Field measurement | [10 empty] | Field measurement
Setup of common support | [14 empty] | Support
[15 empty] | ● | ●
Acc. Beam line
Acc. Area
B4 floor
| ● |  | Crane
| ○ |  | Crane (tentative)
IR work:
Possible with care
IR work:
Forbidden
IR work is forbidden during alignment work.