## Slide 1
Documentation
  Transition to “Production Mode”
  Please update docu and place it to Wiki
    Sensors, ASICs, Assembly, backend electronics &DAQ
Schedule Module/Ladder
TB decision: go on with sensor prod? (!)

## Slide 2
Assemble remaining modules asap!
  practice assembly
  4 Modules for PF (OF) with Taiyo kapton from recent batch (are there enough)
  IF and IB w/o kapton for Probe card qualification
Chipset: SWBv2.1, DCDB4, DHPT1.1
 | W30 | W35 | W36
IF | 0 | 98.44 | 98.96
OF1 | Pilot module 0, H7 | 98.44 | 98.96
OF2 | Pilot module 0, broken | 98.96 | 99.48
OB1 | Pilot module 0 | DESY test 0 | 0
OB2 | Pilot module 0 | 0 | 98.96
IB | DESY test 0 | 0 | 99.48
Module Assignment – PXD9-6 (Pilot)

## Slide 3: Updated schedule – creation of contingency

## Slide 4: Updated schedule – creation of contingency
4 batches: PXD9-7 .. 10
PXD9-7 on schedule
  4 wafers
  almost PXD/2
  For pre-production
PXD9-8 and PXD9-9
  15 wafers for main
  Incl. spares
PXD9-10
  7 wafers
  PF and emergency

## Slide 5: Updated schedule – creation of contingency
SwitcherBv2.1
  Pre-prod available
  Partly bumped, tested
  Re-order 500 more now
DCDB4.1
  First tests okay
  ~ 450 chips available
  12 weeks for more tests
DHPT1.2
  In production at TSMC
  Backup DHPT1.1
  Test as soon as back
  For pre-production
  Order more autumn 16

## Slide 6: Updated schedule – creation of contingency
Kapton
  Qualify Kaupke company
  5 sets Pre-prod ordered
  8-10 w lead time
  Main order asap

## Slide 7: Updated schedule – creation of contingency
Module pre-production: July
  3 L1 and 3 L2 ladders
  Final chip set
  Slowly step-by-step
    FC, SMD, test
  Repeat pilot with larger sample, practice ….

## Slide 8: Updated schedule – creation of contingency
Ladder assembly
  Kapton attach
  Module testing
  Ladder assembly
Phase 2 ladders mid. Oct.
Two spare ladders per layer

## Slide 9: Updated schedule – creation of contingency
Main production, FC, SMD, test
  Start w/ PXD9-8
  Earlier w/ PXD9-7 rem.
  4 modules/week
  6 weeks L1  24 (16)
  8 weeks L2  32 (24)
Kapton attach when L1 done
  Can be earlier
  Testing as soon as module available
  Testing/ladder assembly interleaved

## Slide 10: Updated schedule – creation of contingency
Ladder assembly, Ladder testing, half shell assembly
  ~25 weeks  contingency!!
PXD commissioning at MPP
  3 months  contingency (??)
Shipment to KEK 1 week
  PXD@KEK 12.10.2017

## Slide 11: Summary
Gaining experience with gated mode operation
  Weak points of module periphery of pilot run identified
  More tests needed, optimize operation parameter of DCD
  (very) first tests with analogue CM very promising ….
  Can’t do much more with metal routing on module  go on with sensor production
Updated schedule presented
  First batch sensor production on schedule, in spite delay due to gated mode tests
  Second batch to start this week
  Two phases of module/ladder production:
    Pre-production for phase 2 and spares with fast feedback to IZM (flip-chip)
    Main production in larger batches safes time, creates contingency ….