## Tabelle1
Year | [5 empty] | 2017 | [11 empty] | 2018 | [23 empty] | 2018
Month |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
PXD at KEK
Entrance tests
Prepare PXD installation
SVD Preparation
Transport of SVD halves to B4
Preparation of Beam Pipe
Install PXD Halves on BP + test
Install SVD Halves on HM + test
Common electrical Test with CO2
Cosmic Ray Test in B4
Deinstall cables & PS at B4
Reinstall PS on Belle
Install Cables:Docks to top of Belle
Install VXD + measure position
Connect pipes, cables and cages
Check all connections (local DAQ)
Install bellows
Exercise QCS + RVC (discussion)
Close Endcaps
Close QCS, lock RVC
Close warm dry volume
Turn on CO2
Start Belle-DAQ + some Cosmics
Extra Contingency
Phase 2 / Phase 3
no access to Belle
Access needed