## Slide 1: BEAST2 Test @ DESY SVD Preparation Schedule
Christoph Schwanda (HEPHY Vienna) For the Belle II SVD group
10th VXD Belle II Workshop September 14-16, 2016, Santander, Spain

## Slide 2: Carlos’ proposal
Install SVD DAQ after October BPAC (detector is already @ DESY)
  ~2 weeks of installation/cabling
  Then the system is operated remotely/by the shifter until the testbeam in December
Most critical equipment for this: FADC

## Slide 4: Available FADC systems (as of today until ~March 2017)
FADC v2 @ HEPHY Vienna
  Most important part of the L5 source test stand
  Used for qualifying assembled L5 ladders
FADC v3 @ HEPHY Vienna
  Used by Richard & Hao for hardware/firmware development, debugging
FADC v2 @ KEK
  Used for incoming inspection of L4-L6 @ KEK

## Slide 5: Discussion
Our original idea was to use the FADC system @ KEK for the setup @ DESY from October to December
This would prevent incoming inspection of SVD ladders after shipment to KEK
In the discussion yesterday, there was a consensus that this is very dangerous and could have a significant impact on the SVD ladder mount (damage by shipment is not recognized/repaired in time, thus delaying ladder mount and the overall schedule)
Therefore our proposal now is that SVD DAQ comes only for the beamtest (equipment + manpower), no interference with service installation (different people)

## Slide 6: Study items for SVD
We want to study if FADC v3 or FADC v4 performs better in terms noise (difference is in the LV powering) before starting mass production

## Slide 7: Study items for SVD (2)
I.e., we would like to take data with FADC v3 *and* v4, in the beam or in the permanent setup
The FADC v4 prototype is expected for March 2017

## Slide 8: Thank you