## Slide 1
Design studies
Demonstrator & Prototype magnet
Prototype Integration
Mutiple partners possible
Sep, 2017
~15 months
Mutiple partners possible
of deomsntrator results, negotiations for final magnet production
~24 + 6 months (?)
Dec. 2018
Jun. 2021
~6months (??)
Jun. 2021 ?
Evaluations
Aug. 2021 ?
Final magnet production
~ 80 Months
? 2025 ?
Evaluate how it is most efficient to move on: multiple partners for design, production and characterization?
Magnet Project Time Plan 2018:

## Slide 2
Phase transition innovation partnership: Deliversables
For the demonstrator coil
Technical design for demonstrator & prototype
Procurement of Conductor for demonstrator and prototype (Rutherford cable on copper basis)
Tooling (design and procurement) for winding of coils
Definition of cryogenic interfaces
Production of coil(s)
Testing of demonstrator coil under nominal condition (forces and peak field reached)
For the prototype magnet
Availability of coils for prototype magnet (2 coils)
Power supply system
Design and production of cryostat incl. required testing and certifications
Delivery of Di-pole magnet in cryostat including necessary infrastructure
For demonstrator & prototype:
Technical design report and manufacturing drawings incl. detailed design of final magnet & updated cost estimate

## Slide 3
Phase transition innovation partnership: Offers
Continuation with either one or two innovation partners!
Project coordination & documentation
Technical design of demonstrator coil and prototype magnet (infrastructure, incl. Cryostat, etc.)
Build and test demonstrator
- Procurement of conductor
- Establishing of tooling - Production of coil(s) - Testing of demonstrator coil
Build and deliver prototype (full setup: two coils in cryostat with power supply,
ready to ship)

## Slide 4
As defined in tender documentation:
Assessment factor
Procurement costs of final magnet
Operating costs for final magnet
Construction time for final magnet
Magnet cooling
Interface to haloscope
Shielding of stray magnetic fields
Phase transition innovation partnership: Offers
Continuation with either one or two innovation partners!
Additionally the following criteria will be applied:
Concept for quench protection
Homogeneity of field
Recommendation by external expert committee
Fringe field of prototype magnet
?
?
Evaluation criteria:

## Slide 5
Phase transition innovation partnership:
Continuation without break
 Work while negotiating Phase II (vorweggenommene Durchfühung: premature execution)
Find tasks that are indispensible for Phase II
Order strand: Makes sense if CNRS conductor being used)
Fringe field  Effect on yoke (forces, half opened,..)
Study assembly procedures
….
Needs evaluation by CEA &Noell what can be done

## Slide 6
Phase transition innovation partnership:
External review meeting
Reviewers:
Herman ten Kate – CERN
Stoyan Stoynev – Fermilab
Detleff Sellman – DESY
Fernando Toral Fernandez – CIEMAT
Ramesh Gupta - BNL
Date: Tue 27.Nov. 2018
Location: hamburg, CFEL Building, Seminar room 2
AGENDA:
9:00 – 13:00 CEA Irfu Saclay
14:00 – 18:00 Bilfinger Noell